## Sprint 1
RELEASE PLAN
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS
| SUPREME ERP | Cristiano Politowski | 2021-01-13 | 2021-04-20 |  | 10%
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
| Sprint 1 | Sprint | TEAM 09 | 52 | 2021-01-13 | 2021-02-03 | 21 | Complete
| Documentation | Epic | TEAM 09 | 26 | 2021-01-13 | 2021-02-03 | 21 | In Progress
| Software Architecture Document | Task | Patrick Y. & David R. | 5 | 2021-01-13 | 2021-02-03 | 21 | Complete
| Risk Assessment & Risk Management Plan | Task | Patrick Y. & David R. | 5 | 2021-01-13 | 2021-02-03 | 21 | Complete
| Testing Plan | Task | Phong L. | 3 | 2021-01-13 | 2021-02-03 | 21 | Complete
| Release Plan & Backlog | Task | Sebastien B.N. | 5 | 2021-01-13 | 2021-02-03 | 21 | Complete
| Log in Page UI/UX [Wireframe-Mockup] | Task | Tommy J. & Cosmin S. | 2 | 2021-01-13 | 2021-01-23 | 10 | Complete
| Sidebar menu UI/UX [Wireframe-Mockup] | Task | Tommy J. | 2 | 2021-01-13 | 2021-01-23 | 10 | Complete
| Admin Page UI/UX [Wireframe-Mockup] | Task | Tommy J. | 2 | 2021-01-23 | 2021-02-03 | 11 | In Progress | Moved to Sprint 2
| Products Page UI/UX [Wireframe-Mockup] | Task | Tommy J. | 2 | 2021-01-23 | 2021-02-03 | 11 | In Progress | Moved to Sprint 2
| Set up initial project configuration | Epic | TEAM 09 | 6 | 2021-01-13 | 2021-02-03 | 21 | Complete
| Set up docker | Task | Phong L. | 2 | 2021-01-13 | 2021-01-26 | 13 | Complete
| Set up testing framework | Task | Phong L. | 2 | 2021-01-26 | 2021-02-02 | 7 | Complete
| Set up backend logs | Task | Phong L. | 2 | 2021-01-26 | 2021-02-02 | 7 | Complete
| Sign up / Login | Epic | TEAM 09 | 20 | 2021-01-13 | 2021-02-03 | 21 | In Progress
| Create user model [Database] | Task | Razvan I. | 2 | 2021-01-13 | 2021-01-20 | 7 | Complete
| Implement Sign-up route [Backend] | Task | Razvan I. & Sebastien B.N. | 5 | 2021-01-20 | 2021-02-03 | 14 | Complete
| Implement login route [Backend] | Task | Razvan I. & Sebastien B.N. | 3 | 2021-01-20 | 2021-02-03 | 14 | Complete
| Implement Admin Page [Frontend] | Task | Tommy J. | 5 | 2021-01-20 | 2021-02-03 | 14 | Not Started | Moved to Sprint 2
| Implement Log in Page [Frontend] | Task | Cosmin S. | 5 | 2021-01-20 | 2021-02-03 | 14 | Complete

## Sprint 2
RELEASE PLAN
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS
| SUPREME ERP | Cristiano Politowski | 2021-01-13 | 2021-04-20 |  | 10%
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
| Sprint 2 | Sprint | TEAM 09 | 55 | 2021-02-04 | 2021-02-24 | 20 | In Progress
| Documentation | Epic | TEAM 09 | 17 | 2021-02-04 | 2021-02-24 | 20 | In Progress
| Software Architecture Document (Update) | Task |  | 2 | 2021-02-04 | 2021-02-24 | 20 | Not Started
| Risk Assessment & Risk Management Plan (Update) | Task |  | 2 | 2021-02-04 | 2021-02-24 | 20 | Not Started
| Testing Plan (Update) | Task |  | 2 | 2021-02-04 | 2021-02-24 | 20 | Not Started
| Release Plan & Backlog (Update) | Task |  | 5 | 2021-02-04 | 2021-02-24 | 20 | Not Started
| Products Dashboard UI/UX [Wireframe-Mockup] | Task |  | 2 | 2021-02-04 | 2021-02-24 | 20 | Not Started
| Admin Page UI/UX [Wireframe-Mockup] | Task |  | 2 | 2021-02-04 | 2021-02-24 | 20 | In Progress | Moved from Sprint 1
| Products Page UI/UX [Wireframe-Mockup] | Task |  | 2 | 2021-02-04 | 2021-02-24 | 20 | In Progress | Moved from Sprint 1
| Sign up / Login | Epic | TEAM 09 | 5 | 2021-02-04 | 2021-02-24 | 20 | Not Started
| Implement Admin Page [Frontend] | Task | Tommy J. | 5 | 2021-02-04 | 2021-02-24 | 20 | Not Started | Moved from Sprint 1
| Products | Epic | TEAM 09 | 33 | 2021-02-04 | 2021-02-24 | 20 | Not Started
| Create models for raw materials, semi-finished and finished goods [Database] | Task |  | 5 | 2021-02-04 | 2021-02-06 | 2 | Not Started
| Implement Products Page Dashboard [Backend] | Task |  | 2 | 2021-02-06 | 2021-02-24 | 18 | Not Started
| Implement create/modify/delete for raw materials [Backend] | Task |  | 3 | 2021-02-06 | 2021-02-24 | 18 | Not Started
| Implement create/modify/delete for semi-finished goods [Backend] | Task |  | 3 | 2021-02-06 | 2021-02-24 | 18 | Not Started
| Implement create/modify/delete for finished goods [Backend] | Task |  | 3 | 2021-02-06 | 2021-02-24 | 18 | Not Started
| Implement import/export of product model [Backend] | Task |  | 3 | 2021-02-06 | 2021-02-24 | 18 | Not Started
| Implement Products Page Dashboard [Frontend] | Task |  | 2 | 2021-02-06 | 2021-02-24 | 18 | Not Started
| Implement create/modify/delete for raw materials [Frontend] | Task |  | 3 | 2021-02-06 | 2021-02-24 | 18 | Not Started
| Implement create/modify/delete for semi-finished goods [Frontend] | Task |  | 3 | 2021-02-06 | 2021-02-24 | 18 | Not Started
| Implement create/modify/delete for finished goods [Frontend] | Task |  | 3 | 2021-02-06 | 2021-02-24 | 18 | Not Started
| Implement import/export of product model [Frontend] | Task |  | 3 | 2021-02-06 | 2021-02-24 | 18 | Not Started